## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Vijay | 2025-11-20 | CSV file path incorrect for Indian_Traffic_Violations.csv | Sprint 1 | Vijay | Configuration | Updated file path to correct downloads folder | 2025-11-20 | Closed | Resolved after path correction
2 | Vijay | 2025-11-20 | KeyError: 'Vehicle_Model_Year' while calculating vehicle age | Sprint 1 | Vijay | Code | Verified column name from df.columns and corrected logic | 2025-11-20 | Closed | Template mismatch fixed
3 | Vijay | 2025-11-21 | Time-of-day chart showing wrong ordering of time blocks | Sprint 1 | Vijay | Logic | Explicitly set order=['Morning','Afternoon','Evening','Night'] in countplot | 2025-11-21 | Closed | Order now correct
4 | Vijay | 2025-11-21 | Payment vs Fine bar chart overlapping x‑labels | Sprint 1 | Vijay | UI/UX | Applied plt.tight_layout() and increased figure size | 2025-11-21 | Closed | Chart now readable
5 | Vijay | 2025-11-22 | Severity scores not assigned for unknown violation types | Sprint 2 | Vijay | Logic | Added fillna(5) default severity for unmapped violations | 2025-11-22 | Closed | All rows have severity
6 | Vijay | 2025-11-22 | Groupby insights not printing as tables in expected format | Sprint 2 | Vijay | Code | Wrapped groupby results with reset_index() and renamed columns | 2025-11-22 | Closed | Outputs now clear
7 | Vijay | 2025-11-23 | Weekly offender detection giving empty result due to week calculation issue | Sprint 2 | Vijay | Logic | Used ISO calendar weeks and computed span_weeks correctly | 2025-11-23 | Closed | Now returns valid offenders
8 | Vijay | 2025-11-23 | Agile template .xls could not be read due to xlrd dependency | Sprint 2 | Vijay | Environment | Created separate .xlsx Agile document for the project | 2025-11-23 | Closed | Workaround applied